## Gantt Chart
DIGI - Life Office Extension Project
Galway | Project Start Date: |  | 2022-04-18
Project Lead: | L00169723
Task name | Start date | End date | Owner | Status | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03
Phase One
Initial Documentation | 2022-04-18 | 2022-04-22 | Project Manager | Done
Phase Two
Business proposition | 2022-04-25 | 2022-05-06 | Project Manager | Done
Create scope | 2022-04-27 | 2022-04-29 | Project Manager | Done
Review required standards | 2022-04-29 | 2022-04-29 | Project Manager | Done
Requirements | 2022-05-02 | 2022-05-03 | Project Manager | Done
Phase Three
Identifying resources | 2022-05-09 | 2022-05-11 | Project Manager | Done
Listing required technologies | 2022-05-09 | 2022-05-13 | IT Manager | Done
Providing quoute, pricing | 2022-05-12 | 2022-05-17 | Project Manager | Done
Providing justification | 2020-05-16 | 2022-05-22 | Project Manager | Done
Phase Four
Project risk analysis | 2022-05-16 | 2022-05-18 | Project Manager | Done
Business risk analysis | 2022-05-17 | 2022-05-19 | Project Manager | Done
Monitoring Plan | 2022-06-01 | 2022-06-03 | IT Manager | In progress
Disaster Recovery | 2022-05-30 | 2022-06-01 | Project Manager | Done
Milestones | 2022-05-23 | 2022-05-29 | Project Manager | Done
Phase Five
Procurement of HW | 2022-06-06 | 2022-06-10 | Project Manager | Done
Implementation plan and design | 2022-06-06 | 2022-06-07 | Project Manager | In progress
Creating maintenance plan | 2022-06-08 | 2022-06-09 | IT Manager | In progress
Phase Six
Building physical hosts | 2022-06-10 | 2022-06-13 | IT Manager | Done
Creating base VMs | 2022-06-13 | 2022-06-15 | IT Manager | Done
Installing VM functions | 2022-06-15 | 2022-06-19 | IT Manager | Done
Configuring network | 2022-06-20 | 2022-06-21 | IT Manager | Done
Installing monitoring system | 2022-06-22 | 2022-06-24 | IT Manager | Done
Creating users | 2022-06-24 | 2022-06-25 | IT Manager | In progress
Applying security policies | 2022-06-25 | 2022-06-26 | IT Manager | In progress
Server Hardening | 25/06/200 | 2002-06-26 | IT Manager | In progress
Phase Seven
Configuring phone system | 2022-06-26 | 2022-06-27 | IT Manager | Done
Configuring security cameras | 2022-06-26 | 2022-06-27 | IT Manager | Done
Installing RFID security system. | 2022-06-26 | 2022-06-27 | IT Manager | Done
Phase Eight
Designing test plan | 2022-06-29 | 2022-07-01 | IT Manager | In progress
Implementing test plan | 2022-06-29 | 2022-07-01 | IT Manager | In progress
Last Phase - Project Completion

## Assignees and Status
Assignees | Status
Project Manager | Open
Hardware Supplier | In progress
Software Supplier | Closed
IT Manager | Done
N/A